## Sheet1
| PROJECT NAME | PROJECT MANAGER | START DATE | END DATE |  | OVERALL PROGRESS |  | PROJECT DELIVERABLE
|  |  | 2019-01-22 | 2019-05-11 |  | 20% |  | SCOPE STATEMENT
AT RISK | TASK NAME | FEATURE TYPE | RESPONSIBLE | STORY POINTS | START | FINISH | DURATION (DAYS) | STATUS | COMMENTS
| Sprint 1 |  |  |  | 2019-02-02 | 2019-02-23 | 21 | Complete
| Feature 1 |  |  |  | 2019-02-02 | 2019-02-09 | 7 | Complete
| Feature 2 |  |  |  | 2019-02-07 | 2019-02-16 | 9 | Complete
| Feature 3 |  |  |  | 2019-02-15 | 2019-02-22 | 7 | Overdue
| Sprint 2 |  |  |  | 2019-02-23 | 2019-03-16 | 21 | In Progress
| Feature 4 |  |  |  | 2019-02-23 | 2019-03-01 | 6 | In Progress
| Feature 5 |  |  |  | 2019-02-28 | 2019-03-10 | 10 | Not Started
| Feature 6 |  |  |  | 2019-03-06 | 2019-03-14 | 8 | Not Started
| Sprint 3 |  |  |  | 2019-03-16 | 2019-04-13 | 28 | Not Started
| Feature 7 |  |  |  | 2019-03-16 | 2019-03-26 | 10 | Not Started
| Feature 8 |  |  |  | 2019-03-20 | 2019-04-01 | 12 | Not Started
| Feature 9 |  |  |  | 2019-03-25 | 2019-04-13 | 19 | Not Started
| Sprint 4 |  |  |  | 2019-04-13 | 2019-05-11 | 28 | Not Started
| Feature 10 |  |  |  | 2019-04-13 | 2019-04-20 | 7 | Not Started
| Feature 11 |  |  |  | 2019-04-18 | 2019-05-01 | 13 | Not Started
| Feature 12 |  |  |  | 2019-04-25 | 2019-05-10 | 15 | Not Started